## Project Summary
Project Name | Start Date | End Date | Status | Estimated Budget | Total Estimated Cost | Total Task Costs | Total Expenditures | Total Actual Cost | Budget Variance
solar installation | 2025-07-22 | 2025-09-25 | Completed | 200000.00 | 33134.00 | 200.00000000 | 92507.00 | 92707.00000000 | -107293.00000000

## Tasks
Task ID | Task Name | Parent Task | Type | Status | Planned Start | Planned End | Actual Start | Actual End | Estimated Days | Estimated Cost | Material Cost | Labor Cost | Total Cost | Cost Variance
6 | design | Main Task | Daily | Completed | 2025-07-21 | 2025-07-21 | Not started | 2025-07-21 | 1 | 1500.00 | 0.00 | 200.00000000 | 200.00000000 | -1300.00000000
7 | xyz | Main Task | Weekly | Completed | 2025-07-21 | 2025-07-28 | Not started | 2025-07-21 | 4 | 6000.00 | 0.00 | 0E-8 | 0E-8 | -6000.00000000
8 | design | Main Task | Weekly | Completed | 2025-09-23 | 2025-09-30 | Not started | 2025-09-23 | 7 | 25634.00 | 0.00 | 0E-8 | 0E-8 | -25634.00000000

## Workers
Task ID | Task Name | Worker Name | Specialization | Daily Wage | Assignment Date | Hours Worked | Cost
6 | design | praveen | material provider | 800.00 | 2025-07-21 | 2.00 | 200.00000000

## Materials
Task ID | Task Name | Material Name | Quantity | Unit | Unit Cost | Total Cost | Date Used
7 | xyz | cement | 10.00 | 500 | 25000.00 |  | 2025-07-22

## Expenditures
Date | Description | Category | Amount | Added By
2025-09-23 | Amount paid to Sridhar N S | Permits | 65892.00 | prashanth
2025-09-23 | Amount paid for Electrical Equipments | Materials | 25413.00 | prashanth
2025-09-23 | Amount paid to Technical Notification | Materials | 1202.00 | prashanth

## Cost Summary
Cost Type | Amount
Materials | 0.00
Labor | 200.00000000
Expenditures | 92507.00
Total | 92707.00000000