## Project Summary
Project Name | Start Date | End Date | Status | Estimated Budget | Total Estimated Cost | Total Task Costs | Total Expenditures | Total Actual Cost | Budget Variance
ABC | 2025-05-15 | 2025-11-19 | In Progress | 2300000.00 | 38200.00 | 2550.00000000 | 2541.00 | 5091.00000000 | -2294909.00000000

## Tasks
Task ID | Task Name | Parent Task | Type | Status | Planned Start | Planned End | Actual Start | Actual End | Estimated Days | Estimated Cost | Material Cost | Labor Cost | Total Cost | Cost Variance
1 | clean land grasses | Main Task | Daily | Completed | 2025-07-15 | 2025-07-15 | Not started | 2025-07-17 | 1 | 3500.00 | 0.00 | 1300.00000000 | 1300.00000000 | -2200.00000000
2 | bacement fix | Main Task | Daily | Completed | 2025-07-17 | 2025-07-18 | Not started | In progress | 2 | 8000.00 | 0.00 | 500.00000000 | 500.00000000 | -7500.00000000
3 | dig the land | bacement fix | Daily | Completed | 2025-07-17 | 2025-07-17 | Not started | 2025-07-17 | 1 | 1100.00 | 0.00 | 150.00000000 | 150.00000000 | -950.00000000
5 | aaa | xyz | Daily | Completed | 2025-07-18 | 2025-07-20 | Not started | 2025-07-21 | 3 | 2500.00 | 0.00 | 0E-8 | 0E-8 | -2500.00000000
4 | xyz | Main Task | Daily | Completed | 2025-07-19 | 2025-07-25 | Not started | 2025-07-21 | 12 | 23100.00 | 0.00 | 600.00000000 | 600.00000000 | -22500.00000000

## Workers
Task ID | Task Name | Worker Name | Specialization | Daily Wage | Assignment Date | Hours Worked | Cost
1 | clean land grasses | praveen | material provider | 800.00 | 2025-07-14 | 5.00 | 500.00000000
1 | clean land grasses | praveen | material provider | 800.00 | 2025-07-15 | 8.00 | 800.00000000
3 | dig the land | praveen | material provider | 800.00 | 2025-07-17 | 1.50 | 150.00000000
2 | bacement fix | praveen | material provider | 800.00 | 2025-07-17 | 5.00 | 500.00000000
4 | xyz | praveen | material provider | 800.00 | 2025-07-18 | 6.00 | 600.00000000

## Materials
Task ID | Task Name | Material Name | Quantity | Unit | Unit Cost | Total Cost | Date Used
1 | clean land grasses | cement | 1.00 | 500 | 25000.00 |  | 2025-07-17

## Expenditures
Date | Description | Category | Amount | Added By
2025-05-15 | Food | Materials | 2541.00 | prashanth

## Cost Summary
Cost Type | Amount
Materials | 0.00
Labor | 2550.00000000
Expenditures | 2541.00
Total | 5091.00000000